## Net Zero Projects
THE CORPORATE — NET ZERO ABATEMENT PROJECT REGISTER — 2025–2045
Shadow Carbon Price: | $100 / tCO2e | SBTi Framework: | 1.5°C Aligned | Gross Carbon Debt: | 4,588,079 tCO2e | SBTi Removals Cap: | 458,808 tCO2e | 2030 SBTi Gate: | 784,217 tCO2e (−50% MB) | Max DAC Liability: | $91.8M at $200/t
# | Project Name | Scope(s) | Wave | Status | Max Abatement (tCO2e) | CAPEX ($M) | MAC ($/tCO2e) | OPEX Saving ($M/yr) | Start Year | Target Completion | Primary Facilities | Notes / Trigger
WAVE 1 — 2025–2027 ¦ 7 levers ¦ All MAC ≤ $15/t ¦ Approved for immediate funding ¦ 230,000 tCO2e
1 | Logistics Modal Shift — Air to Sea | Scope 3 | Wave 1 | Approved | 90000 | 0 | -30 | 2.7 | 2025 | 2027 | Shenzhen Systems, Chennai Circuitry | Highest-priority W1 lever. Zero CAPEX. $2.7M annual freight cost saving. Cat 4 reduction.
2 | LED Retrofit & Lighting Controls | Scope 1 & 2 | Wave 1 | In Planning | 15000 | 0.45 | -45 | 0.68 | 2025 | 2026 | All 5 facilities | Rapid payback ~8 months. Immediate electricity reduction across all sites.
3 | Compressed Air Leak Detection | Scope 1 & 2 | Wave 1 | Not Started | 12000 | 0.15 | -65 | 0.78 | 2025 | 2026 | Hanoi Hub, Shenzhen Systems, Chennai Circuitry | Low CAPEX, high ROI. Priority at high-volume production sites.
4 | HVAC Optimisation & AI Sensors | Scope 1 & 2 | Wave 1 | In Planning | 25000 | 1.2 | -25 | 0.63 | 2025 | 2027 | Guadalajara Gigafactory, Shenzhen Systems | Critical for dry room environments at Guadalajara. AI sensor overlay on existing HVAC.
5 | Smart Building Management System | Scope 1 & 2 | Wave 1 | Approved | 33000 | 2.1 | -15 | 0.5 | 2025 | 2027 | All 5 facilities | Central BMS deployment. Integrates LED, HVAC, compressed air monitoring.
6 | On-site Rooftop Solar PV | Scope 2 | Wave 1 | Approved | 45000 | 5.4 | 5 | -0.3 | 2025 | 2027 | Guadalajara Gigafactory (priority), Chennai Circuitry, Hanoi Hub | Guadalajara: 18% solar IRR premium — earliest payback. Chennai: India RPO 25% RE mandate by 2030 — non-discretionary. Hanoi rooftop currently empty — deploy by 2026.
7 | Electric Forklift Fleet Transition | Scope 1 | Wave 1 | Not Started | 10000 | 1.2 | 15 | 0.12 | 2026 | 2027 | Shenzhen Systems, Hanoi Hub | Replaces diesel mobile combustion. Prerequisite: Hanoi battery storage deployment first.
WAVE 2 — 2028–2032 ¦ 5 levers ¦ MAC $20–$85/t ¦ Approved ¦ 400,000 tCO2e
8 | Off-site Virtual PPA — Wind / Solar | Scope 2 | Wave 2 | In Planning | 70000 | 0 | 20 | -0.4 | 2028 | 2032 | Shenzhen Systems (priority), Wrocław Precision | Zero CAPEX. $20/t MAC. Shenzhen: highest grid EF (0.581). Wrocław: EU CBAM pressure raises effective shadow price to $180/t. Largest MB vs LB gap closure.
9 | Supplier Energy Efficiency Program | Scope 3 | Wave 2 | Not Started | 75000 | 0.5 | 25 | 0 | 2028 | 2032 | All facilities — procurement-led | Tier 1 supplier engagement programme. Cat 3 and Cat 1 partial reduction. VP Procurement ownership.
10 | Bio-based Polymers for Packaging | Scope 3 | Wave 2 | Not Started | 80000 | 0 | 55 | 0 | 2028 | 2032 | Shenzhen Systems, Hanoi Hub | Material specification change. Targets Cat 1 polymer inputs. Zero CAPEX — supplier contract renegotiation.
11 | 90% Recycled Aluminium Sourcing | Scope 3 | Wave 2 | In Planning | 140000 | 0 | 80 | 0 | 2028 | 2032 | Wrocław Precision (primary), Shenzhen Systems | Largest single abatement lever in portfolio (140,000 tCO2e). Cat 1 aluminium & metals. Wrocław EU CBAM: $80/t on embodied carbon — effective MAC $180/t raises urgency. VP Procurement lead.
12 | Industrial Heat Pumps | Scope 1 | Wave 2 | Not Started | 35000 | 6.5 | 85 | 0.35 | 2028 | 2032 | Wrocław Precision, Guadalajara Gigafactory | Replaces natural gas for process heat. Wrocław CNC stress-relief ovens primary target. Guadalajara dry rooms secondary.
WAVE 3 — 2033–2040 ¦ 1 lever ¦ MAC = $100/t ¦ WATCH — annual MAC review required ¦ 55,000 tCO2e
13 | Supplier Renewable Energy Mandate (SBTi) | Scope 3 | Wave 3 | Watch | 55000 | 0 | 100 | 0 | 2033 | 2040 | All facilities — Tier 1 & Tier 2 suppliers | MAC exactly at $100/t shadow price threshold. Annual MAC review from 2028 required. Escalate to CSO if MAC > $110/t for 2 consecutive quarters. Cat 3 and Cat 1 supplier energy use.
WAVE 4 — 2040–2045 ¦ DAC removals ¦ $200/t ¦ LAST RESORT — Board approval required ¦ ≤458,808 tCO2e
14 | Permanent Carbon Removals — DAC | Removals | Wave 4 | Not Started | 458808 | 0 | 200 | 0 | 2041 | 2045 | Corporate-level — not facility-specific | LAST RESORT only. SBTi cap: 458,808 tCO2e max (10% gross debt). Max liability $91.8M at $200/t. Board approval required before any DAC contract is executed. Activated only after all operational levers exhausted. Do not exceed cap — triggers mandatory portfolio review.
PORTFOLIO SUMMARY — WAVES 1–3 OPERATIONAL ABATEMENT
| Wave 1 — Approved levers (7) |  |  |  | 230000 | 10.5 |  | 5.11
| Wave 2 — Approved levers (5) |  |  |  | 400000 | 7 |  | -0.05
| Wave 3 — WATCH lever (1) |  |  |  | 55000 | 0 |  | 0
| TOTAL OPERATIONAL ABATEMENT (W1+W2+W3) |  |  |  | 685000 | 17.5 |  | 5.06
PORTFOLIO GAP ANALYSIS vs GROSS CARBON DEBT
| Gross Carbon Debt to 2045 (5% growth, 22yr) |  |  |  | 4588079
| Total Operational Abatement — W1+W2+W3 |  |  |  | 635000
| Maximum DAC Removals — Wave 4 (SBTi cap) |  |  |  | 458808
| Remaining Gap after all levers + DAC |  |  |  | 3494271
| Portfolio coverage of gross debt (%) |  |  |  | 13.8%
Source: The_Corporate_Net_Zero_2045_Strategy_v2.docx — 16 May 2026 — Approved by CSO ¦ Status field is the live element — update as projects progress ¦ Blue = inputs ¦ Black = formulas ¦ MAC: negative = cost saving

## Emission Factors
EMISSION FACTORS — 2023 BASELINE
Factor Name | Value | Unit | Scope / Category | Notes
Natural Gas | 0.002034 | tCO2e / m³ | S1 Stationary | IPCC AR6 — incl. CH4 & N2O
Diesel (stationary) | 2.68 | tCO2e / tonne | S1 Stationary | IEA 2023
LPG | 1.54 | tCO2e / tonne | S1 Stationary | IPCC default
Coal (thermal) | 2.42 | tCO2e / tonne | S1 Stationary | IPCC 2006 GL
Diesel (mobile) | 2.653 | tCO2e / tonne | S1 Mobile | GHG Protocol
Petrol (mobile) | 2.31 | tCO2e / tonne | S1 Mobile | GHG Protocol
Grid — Vietnam | 0.4936 | tCO2e / MWh | S2 Electricity | IEA 2022 VN grid
Grid — Mexico | 0.454 | tCO2e / MWh | S2 Electricity | SEMARNAT 2022
Grid — China | 0.581 | tCO2e / MWh | S2 Electricity | CEA 2022
Grid — Poland | 0.726 | tCO2e / MWh | S2 Electricity | KOBiZE 2022
Grid — India | 0.708 | tCO2e / MWh | S2 Electricity | CEA India 2022
Renewable (PPA/REC) | 0 | tCO2e / MWh | S2 Market-based | GHG Protocol MB method
Note: All factors are mock/illustrative values for dashboard modelling. Replace with certified factors for compliance reporting.

## Scope 1 — Detail
SCOPE 1 EMISSIONS & ENERGY CONSUMPTION — 2023
| STATIONARY COMBUSTION | [6 empty] | MOBILE COMBUSTION
Facility | Nat. Gas (m³) | Nat. Gas (tCO2e) | Diesel Stat. (t) | Diesel Stat. (tCO2e) | LPG (t) | LPG (tCO2e) | Total Stationary (tCO2e) | Diesel Mobile (t) | Diesel Mobile (tCO2e) | Petrol Mobile (t) | Total Mobile (tCO2e)
Hanoi Hub | 2800000 | 5695.2 | 0 | 0 | 120 | 184.8 | 5880 | 85 | 225.505 | 30 | 294.805
Guadalajara Gigafactory | 1400000 | 2847.6 | 0 | 0 | 60 | 92.4 | 2940 | 55 | 145.915 | 20 | 192.115
Shenzhen Systems | 3500000 | 7119 | 0 | 0 | 80 | 123.2 | 7242.2 | 190 | 504.07 | 95 | 723.52
Wrocław Precision | 1900000 | 3864.6 | 0 | 0 | 220 | 338.8 | 4203.4 | 40 | 106.12 | 15 | 140.77
Chennai Circuitry | 1200000 | 2440.8 | 680 | 1822.4 | 40 | 61.6 | 4324.8 | 75 | 198.975 | 25 | 256.725
TOTAL | 10800000 | 21967.2 | 680 | 1822.4 | 520 | 800.8 | 24590.4 | 445 | 1180.585 | 185 | 1607.935

## Scope 2 — Detail
SCOPE 2 EMISSIONS & ENERGY CONSUMPTION — 2023
| ELECTRICITY CONSUMPTION |  |  |  |  | LOCATION-BASED |  | MARKET-BASED
Facility | Total Elec. (MWh) | Grid Elec. (MWh) | Renewables PPA (MWh) | % Renewable | Gas EF Applied | LB Emissions (tCO2e) | LB Intensity (tCO2e/MWh) | MB Emissions (tCO2e) | MB Intensity (tCO2e/MWh)
Hanoi Hub | 58000 | 50000 | 8000 | 13.79% | EF:B9 | 28628.8 | 0.4936 | 24680 | 0.42552
Guadalajara Gigafactory | 72000 | 50000 | 22000 | 30.56% | EF:B10 | 32688 | 0.454 | 22700 | 0.31528
Shenzhen Systems | 94000 | 88000 | 6000 | 6.383% | EF:B11 | 54614 | 0.581 | 51128 | 0.54391
Wrocław Precision | 31000 | 22000 | 9000 | 29.03% | EF:B12 | 22506 | 0.726 | 15972 | 0.51523
Chennai Circuitry | 41000 | 37000 | 4000 | 9.756% | EF:B13 | 29028 | 0.708 | 26196 | 0.63893
TOTAL | 296000 | 247000 | 49000 | 16.55% |  | 167464.8 | 0.59252 | 140676 | 0.48777

## Scope 3 — Detail
SCOPE 3 EMISSIONS — CATEGORY BREAKDOWN — 2023
Category | Hanoi Hub | Guadalajara Gigafactory | Shenzhen Systems | Wrocław Precision | Chennai Circuitry | TOTAL
── UPSTREAM ──
Cat 1: Purchased Goods & Services | 128400 | 89200 | 312000 | 42100 | 156800 | 728500
Cat 2: Capital Goods | 8200 | 11400 | 14600 | 9800 | 7200 | 51200
Cat 3: Fuel & Energy-Related | 4100 | 5800 | 9200 | 3600 | 4900 | 27600
Cat 4: Upstream Transportation | 22100 | 18600 | 48200 | 12400 | 31600 | 132900
Cat 5: Waste Generated in Ops | 1200 | 980 | 2400 | 640 | 1800 | 7020
Cat 6: Business Travel | 420 | 380 | 880 | 310 | 540 | 2530
Cat 7: Employee Commuting | 3200 | 2600 | 8400 | 1800 | 4200 | 20200
Cat 8: Upstream Leased Assets | 600 | 400 | 900 | 200 | 700 | 2800
── DOWNSTREAM ──
Cat 9: Downstream Transport | 9800 | 7200 | 24600 | 4100 | 14200 | 59900
Cat 10: Processing of Sold Prods | 0 | 0 | 0 | 0 | 0 | 0
Cat 11: Use of Sold Products | 42000 | 68000 | 110000 | 12000 | 88000 | 320000
Cat 12: End-of-Life Treatment | 6400 | 8200 | 18400 | 2200 | 12600 | 47800
Cat 13: Downstream Leased Assets | 200 | 150 | 400 | 80 | 280 | 1110
Cat 14: Franchises | 0 | 0 | 0 | 0 | 0 | 0
Cat 15: Investments | 0 | 0 | 0 | 0 | 0 | 0
TOTAL SCOPE 3 (tCO2e) | 226620 | 212910 | 549980 | 89230 | 322820 | 1401560

## Energy Mix
ENERGY MIX & CONSUMPTION DETAIL — 2023
Facility | Nat. Gas (MWh eq.) | Diesel Stat. (MWh eq.) | LPG (MWh eq.) | Total Fossil Thermal (MWh eq.) | Grid Electricity (MWh) | Renewable Electricity (MWh) | Total Electricity (MWh) | Total Energy (MWh eq.)
Hanoi Hub | 29540 | 0 | 1572 | 31112 | 50000 | 8000 | 58000 | 89112
Guadalajara Gigafactory | 14770 | 0 | 786 | 15556 | 50000 | 22000 | 72000 | 87556
Shenzhen Systems | 36925 | 0 | 1048 | 37973 | 88000 | 6000 | 94000 | 131973
Wrocław Precision | 20045 | 0 | 2882 | 22927 | 22000 | 9000 | 31000 | 53927
Chennai Circuitry | 12660 | 7908.4 | 524 | 21092.4 | 37000 | 4000 | 41000 | 62092.4
TOTAL | 113940 | 7908.4 | 6812 | 128660.4 | 247000 | 49000 | 296000 | 424660.4

## Master Summary
THE CORPORATE — EMISSIONS & ENERGY MASTER SUMMARY — 2023
Facility | S1 Stationary (tCO2e) | S1 Mobile (tCO2e) | Total Scope 1 (tCO2e) | S2 LB (tCO2e) | S2 MB (tCO2e) | S1+S2 LB (tCO2e) | Scope 3 (tCO2e) | Total GHG LB (tCO2e) | Total Electricity (MWh) | % Renewable
Hanoi Hub (Vietnam) | 5880 | 294.805 | 6174.805 | 28628.8 | 24680 | 34803.605 | 226620 | 261423.605 | 58000 | 13.79%
Guadalajara Gigafactory (Mexico) | 2940 | 192.115 | 3132.115 | 32688 | 22700 | 35820.115 | 212910 | 248730.115 | 72000 | 30.56%
Shenzhen Systems (China) | 7242.2 | 723.52 | 7965.72 | 54614 | 51128 | 62579.72 | 549980 | 612559.72 | 94000 | 6.383%
Wrocław Precision (Poland) | 4203.4 | 140.77 | 4344.17 | 22506 | 15972 | 26850.17 | 89230 | 116080.17 | 31000 | 29.03%
Chennai Circuitry (India) | 4324.8 | 256.725 | 4581.525 | 29028 | 26196 | 33609.525 | 322820 | 356429.525 | 41000 | 9.756%
COMPANY TOTAL | 24590.4 | 1607.935 | 26198.335 | 167464.8 | 140676 | 193663.135 | 1401560 | 1595223.135 | 296000 | 16.55%
KEY PERFORMANCE INDICATORS
Total Scope 1+2 (LB) tCO2e |  |  | 193663.135
Total Scope 3 tCO2e |  |  | 1401560
Total GHG (all scopes) tCO2e |  |  | 1595223.135
Total Electricity MWh |  |  | 296000
Corporate Renewable % |  |  | 16.55%

## Data Dictionary
DATA DICTIONARY — THE CORPORATE EMISSIONS MODEL
Field / Column | Description | Unit | Sheet | Notes
Nat. Gas Consumed | Volume of natural gas consumed in stationary combustion | m³ | S1 Detail | Boilers, furnaces, dryers
Nat. Gas Emissions | CO2e from natural gas × emission factor | tCO2e | S1 Detail | EF: 0.002034 tCO2e/m³
Diesel (Stationary) | Diesel fuel for backup generators and stationary engines | tonnes | S1 Detail | Key for Chennai (grid instability)
Diesel (Mobile) | Diesel for forklifts, on-site vehicles | tonnes | S1 Detail | EF: 2.653 tCO2e/t
Petrol (Mobile) | Petrol/gasoline for on-site light vehicles | tonnes | S1 Detail | EF: 2.31 tCO2e/t
Total Stationary S1 | Sum of all stationary combustion emissions | tCO2e | S1 Detail | Formula: nat gas + diesel + LPG
Total Mobile S1 | Sum of all mobile combustion emissions | tCO2e | S1 Detail | Formula: diesel mob + petrol mob
Total Electricity | Total electricity consumed (grid + renewables) | MWh | S2 Detail | Includes PPA/REC volumes
Grid Electricity | Electricity from national grid (location-based) | MWh | S2 Detail | Grid elec = Total minus Renewables PPA
Renewables PPA | Electricity covered by PPAs or RECs | MWh | S2 Detail | Zero-carbon under market-based
LB Emissions | Location-based S2: all elec × country grid EF | tCO2e | S2 Detail | GHG Protocol location method
MB Emissions | Market-based S2: grid-only elec × country EF | tCO2e | S2 Detail | Renewables = 0 tCO2e/MWh
Cat 1 — Purch. Goods | Purchased raw materials: plastics, metals, chemicals | tCO2e | S3 Detail | Spend-based estimation
Cat 4 — Upstream Tpt | Inbound freight, logistics to facilities | tCO2e | S3 Detail | Distance × weight method
Cat 11 — Use of Prods | In-use electricity consumption of sold chargers/batteries | tCO2e | S3 Detail | Largest downstream category
Nat. Gas (MWh eq.) | Natural gas volume converted to MWh equivalent | MWh | Energy Mix | Factor: 0.01055 MWh/m³ (HHV)
Diesel (MWh eq.) | Diesel converted to MWh equivalent | MWh | Energy Mix | Factor: 11.63 MWh/tonne
LPG (MWh eq.) | LPG converted to MWh equivalent | MWh | Energy Mix | Factor: 13.10 MWh/tonne